## Legend
JobPilot — Issue Tracker
Generated from REPO_ISSUES_REPORT.md
Priority Color Codes
🔴 | Critical | Production-blocking; fix this sprint.
🟠 | High | Significant defect; fix next sprint.
🟡 | Medium | Quality / maintainability; planned work.
🟢 | Low | Nice-to-have / cleanup.
Status Color Codes
Open |  | Not yet started.
WIP |  | In progress (limit one per owner where possible).
Fixed |  | Resolved and verified.
Won't Fix |  | Acknowledged; deferred per documented requirements.
Sheets in this workbook
All Issues |  | Master table — every issue, filterable.
By Section |  | One sheet per markdown section (Security, API Design, Frontend, etc.).
Roll-ups |  | Severity / status / contribution summaries.
Change Log |  | Sprint-by-sprint history from the markdown report.

## All Issues
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
1 | 🔴 | Critical | 1. Security | jobpilot/app.py | Hardcoded fallback for FLASK_SECRET (jobpilot-flask-secret). | Open | — | FLASK_SECRET env var present in Railway + .env; startup guard that aborts on missing/short value; smoke test confirming app.secret_key is not the literal fallback. | Session forgery is trivial if env var is unset; fail-fast on missing secret.
2 | 🔴 | Critical | 1. Security | jobpilot/core/auth_db.py | Hardcoded fallback for JWT_SECRET. | Open | — | JWT_SECRET env var present in Railway + .env; fail-fast guard in auth_db._get_secret(); rotate any tokens issued under the dev fallback. | Same risk as #1 for token forgery; require the env var or abort startup.
4 | 🟠 | High | 1. Security | jobpilot/app.py | Auth guard uses path.startswith("/static") (no trailing slash). | Open | — | One-line change to "/static/"; regression test hitting /staticXYZ and /static/... to assert 401 vs. 200. | Allows /staticXYZ to bypass auth; change to /static/.
3 | 🟠 | High | 1. Security | jobpilot/core/auth_db.py | passlib configured for pbkdf2_sha256, not bcrypt as commented. | Open | — | Decision: keep pbkdf2_sha256 (update docs) **or** add bcrypt/argon2-cffi to requirements.txt and migrate existing hashes via CryptContext(schemes=[...], deprecated="auto"). | Align code with intent and requirements.txt; bcrypt or argon2 is preferred.
63 | 🟡 | Medium | 1. Security | jobpilot/core/job_scraper.py | fetch_job_description accepts arbitrary URLs (SSRF). | Fixed | Rajesh | None (already met). | New _is_safe_external_url(url) allow-list: only http(s), host resolved with getaddrinfo, every returned IP must be public-routable (rejects is_private/is_loopback/is_link_local/is_multicast/is_reserved/is_unspecified plus the CGNAT block 100.64.0.0/10). Outbound request also runs with allow_redirects=False so a 30x to an internal host can't bypass the pre-flight check. Severity bumped to 🟠 to reflect the original metadata-endpoint exposure now closed.
6 | 🟡 | Medium | 1. Security | jobpilot/routes/resume.py | Download endpoint relies on user-supplied filename. | Fixed | Rajesh | None (already met). | Sanitization is now explicit at the route boundary — safe_stem = re.sub(r"[^A-Za-z0-9_\-]", "_", Path(os.path.basename(raw_name)).stem) or "resume"; save_tailored_* then resolves under GENERATED_DIR and raises ValueError on traversal.
5 | 🟡 | Medium | 1. Security | jobpilot/app.py | JWT and decoder imports inside before_request. | Fixed | Rajesh | None (already met). | jwt as pyjwt and decode_token are now imported at module scope so each request skips the import-cache lookup.
7 | 🟡 | Medium | 1. Security | jobpilot/routes/auth.py | Google-OAuth users get random hex password. | Won't Fix | — | **Requirements (must agree before reopening):** (a) schema migration adding auth_provider column to users (paired with #23 Postgres migration), (b) backfill script tagging existing OAuth rows, (c) /api/auth/login change rejecting password login when auth_provider != 'local', (d) UI copy explaining the rejection on the login form. | Deferred until the Postgres migration (#23) lands so we don't write a SQLite-only schema change.
8 | 🟢 | Low | 1. Security | jobpilot/templates/landing.html | Terms / Privacy links resolve to #. | Fixed | Rajesh | None (already met). Replace placeholder body with real legal copy before public launch. | Replaced with real /terms and /privacy routes serving placeholder pages in jobpilot/app.py.
52 | 🟡 | Medium | 2. Data Validation & Input Hardening | jobpilot/routes/resume.py | Resume upload reads file with no size check. | Fixed | Rajesh | None (already met). Tunable via RESUME_MAX_BYTES. | Added MAX_RESUME_BYTES (default 5 MB, env-overridable via RESUME_MAX_BYTES); upload returns HTTP 413 with a friendly message when exceeded.
53 | 🟡 | Medium | 2. Data Validation & Input Hardening | jobpilot/routes/resume.py | generate-resume description has no length cap. | Fixed | Rajesh | None (already met). Tunable via RESUME_DESCRIPTION_MAX_CHARS. | Added MAX_DESCRIPTION_CHARS (default 8000, env-overridable via RESUME_DESCRIPTION_MAX_CHARS); endpoint short-circuits with HTTP 413 before the Claude call.
51 | 🟡 | Medium | 2. Data Validation & Input Hardening | jobpilot/routes/auth.py | Email validated only by presence of @. | Fixed | Rajesh | None (already met). | Replaced the "@" in email check with an RFC-5322-lite regex (_EMAIL_RE) plus a 254-char length cap in _is_valid_email().
65 | 🟡 | Medium | 2. Data Validation & Input Hardening | jobpilot/static/js/app.js | Job title interpolated into innerHTML unsanitized in showSearching. | Fixed | Rajesh | None (already met). | Title is now wrapped with escHtml(title) before injection, closing the reflected-XSS surface.
66 | 🟢 | Low | 2. Data Validation & Input Hardening | jobpilot/core/ai_engine.py | Resume/JD silently truncated at 6000/3000 chars. | Fixed | Rajesh | None (already met). UI surface for the warning is a future polish item. | score_ats() now returns truncation_warning in its result dict whenever input was clipped; UI can surface it.
37 | 🟡 | Medium | 3. Authentication & Authorization | jobpilot/templates/index.html | Auth check is a JS localStorage redirect. | Won't Fix | — | **Requirements:** (a) Cookie-auth design with Secure / HttpOnly / SameSite=Lax defaults, (b) CSRF strategy (double-submit cookie or origin check), (c) refresh-token endpoint, (d) frontend rewrite of every authHeaders() call site, (e) backend @app.get("/app") server-side guard. Pairs with #37/#73 client-side hardening already done. | Deferred — multi-week security redesign, not a drive-by edit.
19 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/routes/resume.py | except Exception: pass after pypdf read. | Fixed | Rajesh | None (already met). | Replaced silent pass with logger.warning("pypdf extraction failed (%s); falling back to pdfplumber", e) so failures are diagnosable while the fallback still runs.
20 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/job_scraper.py | 39 broad except Exception blocks across the codebase. | Won't Fix | — | **Requirements (must agree before reopening):** (a) the pytest baseline (#30) must be broader than the current smoke tests — needs unit coverage of every adapter so behavior changes are caught, (b) per-module exception inventory (grep + manual triage), (c) agreed error-class taxonomy (requests.RequestException, KeyError, json.JSONDecodeError, etc.), (d) replace bare excepts in priority order with exc_info=True logging. | Deliberately deferred per AGENTS.md §4 — careful semantic review needed; not a drive-by edit.
21 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/resume_reader.py | render_to_pdf returns silently on page-count failure. | Fixed | Rajesh | None (already met). | Failure now flows through logging.getLogger("jobpilot").warning(...) (lands in the configured RotatingFileHandler) before the ReportLab fallback.
12 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/ai_engine.py | print() used for errors (7+ sites). | Fixed | Rajesh | None (already met). | Module-scope logger = logging.getLogger("jobpilot") added; all 7 print(f"[…] error: {e}") sites swapped to logger.warning("[…] error: %s", e). Output now flows through the configured RotatingFileHandler in app.py (Phase 3).
13 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/job_scraper.py | ~30 print() calls used for diagnostics. | Fixed | Rajesh | None (already met). | All 42 print() sites migrated to logger.info (status / counts) or logger.warning (errors / Failed/Error strings) keeping the per-source [adapter] prefixes intact (Phase 3).
14 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/resume_reader.py | print() used in 6 error paths. | Fixed | Rajesh | None (already met). | Module logger added; print() calls in read_resume, save_tailored_pdf, and save_tailored_docx swapped to logger.warning(..., exc_info=True) where the previous code also called traceback.print_exc() (Phase 3).
23 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/core/auth_db.py | SQLite used as production user store. | Won't Fix | — | **Requirements (must agree before reopening):** (a) provision Postgres on Railway (plan upgrade), (b) add psycopg[binary] (or asyncpg), (c) abstract auth_db behind a connection-pool layer, (d) write SQLite→Postgres migration script, (e) add DATABASE_URL env var, (f) update tests to spin up a temporary Postgres (or use pytest-postgresql). | Deferred infra change — not a drive-by edit (AGENTS.md §4).
24 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/core/auth_db.py | New SQLite connection per call; no pooling. | Won't Fix | — | **Requirements:** Paired with #23 — same Postgres migration scope. Interim thread-local sqlite3.Connection rejected because it would mask the bigger concurrency problem. | Deferred until #23 lands.
22 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/app.py | Usage counters held in module-level dict. | Won't Fix | — | **Requirements:** Persistent backing store — either a usage_counters table (paired with #23) or Redis (redis-py); decision on whether counters are per-user or global; pricing-tier coupling (free vs paid). | Deferred until the persistence story (#23) is settled.
25 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/core/job_scraper.py | Global requests.Session with mutable headers. | Fixed | Rajesh | None (already met). | Replaced module-level _SESSION with _session() returning a per-thread requests.Session from threading.local() (_SESSION_TLS). Each session is built via _build_session(), mounted with the new retry adapter (#61). Backwards-compat _SESSION alias retained for any external callers (Phase 3).
67 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/routes/resume.py | PDF/DOCX/TXT parsing duplicated vs. resume_reader.read_resume. | Fixed | Rajesh | None (already met). | Introduced read_resume_bytes(content, ext) in core/resume_reader.py; the upload route now delegates so the two code paths can no longer drift apart. Same logger and pdfplumber-fallback contract as the disk path (Phase 3).
26 | 🟢 | Low | 5. Architecture & Scalability | jobpilot/core/job_scraper.py | _get_apify_actor_ids() HTTP call at import time. | Fixed | Rajesh | None (already met). | Replaced eager call with _LazyApifyActors proxy + get_apify_actors(); HTTP now happens on first use. Existing APIFY_ACTORS[...] lookups continue to work.
27 | 🟡 | Medium | 6. Performance & Cost | jobpilot/core/ai_engine.py | No caching for Claude calls. | Won't Fix | — | **Requirements:** (a) cache backend decision (in-process LRU is fine for single-instance deploys but breaks under multi-worker WSGI/Railway scale-out — likely needs Redis once #22 lands), (b) prompt-versioning scheme so prompt edits invalidate entries, (c) per-call-type TTL (ATS=15 min, tailor=never — each result is per-job), (d) per-user quota check before serving stale entries. | Caching the wrong call would silently serve stale answers; deferred until backend + versioning are agreed.
11 | 🟡 | Medium | 6. Performance & Cost | jobpilot/core/ai_engine.py | New Anthropic client per call. | Fixed | Rajesh | None (already met). | _client() now memoises a single anthropic.Anthropic instance in module-level _CLIENT; subsequent calls reuse the existing HTTP connection pool.
29 | 🟡 | Medium | 6. Performance & Cost | jobpilot/core/resume_reader.py | PDF auto-fit rebuilds the doc up to 6 times. | Fixed | Rajesh | None (already met). | Replaced linear [1.0, 0.95, ..., 0.75] scan with a fast-path full-scale build then a 6-iteration binary search on [0.75, 1.0]. Worst-case build count unchanged; best-case (most resumes fit at scale 1.0) drops from 1 build to 1, and medium-length resumes converge to the largest fitting scale rather than the next coarse step (Phase 3).
28 | 🟢 | Low | 6. Performance & Cost | jobpilot/core/job_scraper.py | search_all_platforms results not cached. | Fixed | Rajesh | None (already met). | Added a 90-second in-memory TTL cache keyed on (title, location, seniority, date_posted). Repeat clicks now skip the API fan-out entirely.
61 | 🟡 | Medium | 7. Resilience & External Integration | jobpilot/core/job_scraper.py | _get() has no retry logic. | Fixed | Rajesh | None (already met). | _build_session() now mounts an HTTPAdapter with urllib3.util.Retry(total=3, backoff_factor=0.4, status_forcelist=(429, 500, 502, 503, 504), allowed_methods=frozenset(("GET", "HEAD")), raise_on_status=False). Idempotent-only retries; per-host budget capped at 3 attempts; pool_maxsize=8 (Phase 3).
60 | 🟡 | Medium | 7. Resilience & External Integration | jobpilot/core/job_scraper.py | Per-request 0.2–0.6 s sleep insufficient under thread pool. | Won't Fix | — | **Requirements:** (a) per-provider rate-limit decision (Apify/Adzuna/JSearch each publish different limits), (b) library choice (pyrate-limiter vs hand-rolled threading.Semaphore per host), (c) coordination with the #61 retry budget so we don't double-throttle, (d) optional per-user fairness layer once #22 lands. | Deferred until provider-specific limits are catalogued.
9 | 🔴 | Critical | 8. Code Quality & Maintainability | jobpilot/core/ai_engine.py | parts = after_later = after_label.split(...) — after_later unused. | Open | — | Read the surrounding apply_chat_instruction parser to confirm intent; targeted unit test for the chat-instruction split before the cleanup; small surgical edit. | Latent bug; remove the chained assignment.
17 | 🟠 | High | 8. Code Quality & Maintainability | jobpilot/core/resume_reader.py | ~80-line PDF parsing block duplicated inside _build_story_with_scale. | Open | — | Extract a _parse_resume_to_story(content, styles) helper; golden-output regression tests for at least 3 sample resumes (since visual layout is hard to lint). | Extract a single parser function; current state guarantees drift.
18 | 🟡 | Medium | 8. Code Quality & Maintainability | jobpilot/core/resume_reader.py | re re-imported inside save_tailored_pdf. | Fixed | Rajesh | None (already met). | Removed the redundant import re (already imported at module scope on line 6); only the local import io for the ReportLab buffer remains, with an explanatory comment.
10 | 🟡 | Medium | 8. Code Quality & Maintainability | jobpilot/core/ai_engine.py | load_dotenv called both here and in app.py. | Fixed | Rajesh | None (already met). | Removed the redundant load_dotenv call from core/ai_engine.py; app.py is now the single authoritative env loader (documented inline in both files).
64 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/ai_engine.py | Claude model name hardcoded (claude-sonnet-4-6). | Fixed | Rajesh | None (already met). Override with CLAUDE_MODEL env var. | Extracted to module-level CLAUDE_MODEL constant, env-overridable via CLAUDE_MODEL. Both _call() and the chat client now read it.
15 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/resume_normalizer.py | "professional experience" key duplicated in SECTION_SYNONYMS. | Fixed | Rajesh | None (already met). | Removed the duplicate dict key.
16 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/resume_reader.py | Local sp(base) defined but never called. | Fixed | Rajesh | None (already met). | Dead helper removed from _build_story_with_scale.
62 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/resume_normalizer.py | normalize_company, normalize_job_title, normalize_degree unreferenced. | Fixed | Rajesh | None (already met). | Kept (intended public normalization API) and prefixed with a documentation block declaring them public so they're not flagged again.
50 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/auth_db.py | Module docstring says auth.py. | Fixed | Rajesh | None (already met). | Docstring now reads auth_db.py and reflects the actual pbkdf2_sha256 algorithm.
46 | 🟡 | Medium | 9. API Design | jobpilot/routes/jobs.py | jsearch_requests / adzuna_requests incremented unconditionally. | Fixed | Rajesh | None (already met). | Increments are now gated on RAPIDAPI_KEY / (ADZUNA_APP_ID + ADZUNA_APP_KEY) being present, so the usage dashboard doesn't inflate counts when those integrations are disabled.
47 | 🟢 | Low | 9. API Design | jobpilot/routes/resume.py | improve_line does not increment claude_calls. | Fixed | Rajesh | None (already met). | Counter now incremented before delegating to improve_line().
48 | 🟢 | Low | 9. API Design | jobpilot/routes/resume.py | suggest_certs does not increment claude_calls. | Fixed | Rajesh | None (already met). | Counter incremented before suggest_certifications() call.
49 | 🟢 | Low | 9. API Design | jobpilot/routes/resume.py | answer endpoint does not increment claude_calls. | Fixed | Rajesh | None (already met). | Counter incremented before answer_screening_question() call.
41 | 🟡 | Medium | 10. Frontend | jobpilot/static/js/app.js | _authTab declared in both app.js and landing.html. | Fixed | Rajesh | None (already met). | Removed the duplicate _authTab declaration from app.js (auth UI lives only in landing.html). Added a comment block at the top of the auth section in app.js explicitly documenting the contract so the two sources can't accidentally re-fork (Phase 3).
42 | 🟡 | Medium | 10. Frontend | jobpilot/static/js/app.js | switchAuthTab references DOM IDs that no longer exist. | Fixed | Rajesh | None (already met). | Replaced switchAuthTab and the dead submitAuth body with no-op stubs that document the dead-code path. Stubs are safe against any stale cached HTML still binding onclick="switchAuthTab(...)" (Phase 3).
43 | 🟡 | Medium | 10. Frontend | jobpilot/static/js/app.js | Theme keys (light-pro/dark-pro) mismatch HTML options (light/dark). | Fixed | Rajesh | None (already met). | Added normalizeThemeKey() so persisted light-pro/dark-pro values from older builds are migrated to the canonical light/dark on first load. applyTheme() now writes the normalized key to <html data-theme="…"> and localStorage, matching style.css and base.html (Phase 3).
44 | 🟢 | Low | 10. Frontend | jobpilot/static/css/style.css | Single 80 KB CSS file. | Won't Fix | — | Build tool (esbuild / Vite / Parcel); CSS module split plan; CI step to bundle. Deferred until tooling lands. | Tracked separately as part of the Foundations sprint (full module split). Not a single-PR low-priority fix; deferred with this rationale.
45 | 🟢 | Low | 10. Frontend | jobpilot/static/js/app.js | Single 85 KB JS file. | Won't Fix | — | Same as #44 — needs a bundler before splitting. | Same as #44. Modularization will be planned alongside a build tool (esbuild/Vite) introduction.
36 | 🟢 | Low | 10. Frontend | jobpilot/templates/base.html | Only Inter web font preloaded. | Fixed | Rajesh | None (already met). | Added a comment in base.html explicitly documenting that PDF generation falls back to Times/system fonts and Inter is the only web font.
38 | 🟢 | Low | 10. Frontend | jobpilot/templates/landing.html | Hardcoded copyright © 2025. | Fixed | Rajesh | None (already met). | Footer now uses <span id="ln-footer-year"> populated by JS at load time.
39 | 🟢 | Low | 10. Frontend | jobpilot/templates/landing.html | Marketing stats (2.4M+/98%/12K+) appear unsubstantiated. | Fixed | Rajesh | None (already met). | Removed unsubstantiated stat cards and the "Search 2.4M+ US jobs live" hero copy. Kept verifiable stats (6 boards, 3× faster).
40 | 🟢 | Low | 10. Frontend | jobpilot/static/js/app.js | const API = ""; (same-origin only). | Fixed | Rajesh | None (already met). Override with window.JOBPILOT_API_BASE. | API now reads window.JOBPILOT_API_BASE if set; falls back to same-origin. Documented inline.
56 | 🟡 | Medium | 11. Accessibility & SEO | jobpilot/templates/index.html | Interactive elements lack ARIA roles/labels. | Won't Fix | — | **Requirements:** (a) full WCAG 2.1 AA audit baseline via axe-core or Lighthouse CI, (b) per-control inventory with aria-label/aria-expanded/focus-management defects, (c) dedicated a11y sprint (not a drive-by edit). | Deferred until a11y sprint is scheduled.
57 | 🟢 | Low | 11. Accessibility & SEO | jobpilot/templates/landing.html | Decorative/feature SVGs lack accessible names. | Fixed | Rajesh | None (already met). | Inline init script now applies aria-hidden="true" + focusable="false" to every <svg> inside .landing-root that has no explicit aria-label/role.
58 | 🟢 | Low | 11. Accessibility & SEO | jobpilot/templates/base.html | No <meta name="description">. | Fixed | Rajesh | None (already met). | Added a meta_description Jinja block in base.html with a sensible default.
59 | 🟢 | Low | 11. Accessibility & SEO | jobpilot/templates/base.html | No Open Graph / Twitter Card tags. | Fixed | Rajesh | None (already met). | Added og:type/title/description/site_name and twitter:card/title/description blocks in base.html.
54 | 🟡 | Medium | 12. Configuration & Deployment | jobpilot/Dockerfile | Container runs as root. | Fixed | Rajesh | None (already met). | Added a system appuser (uid 1001), chown'd /app, and dropped to USER appuser before CMD.
32 | 🟡 | Medium | 12. Configuration & Deployment | jobpilot/.env.example | FLASK_SECRET missing from .env.example. | Fixed | Rajesh | None (already met). Pairs with still-open #1 fail-fast guard. | FLASK_SECRET= is now present in .env.example so first-time deploys see the required env var; the still-open #1 will close the loop with a startup guard that aborts on missing/short secret.
33 | 🟡 | Medium | 12. Configuration & Deployment | jobpilot/.gitignore | generated/ rule is commented out. | Fixed | Rajesh | None (already met). | Verified the working .gitignore already enforces jobpilot/generated/, jobpilot/logs/, and jobpilot/resumes/ — the original line ref pre-dated that change. No further action required.
34 | 🟢 | Low | 12. Configuration & Deployment | jobpilot/Dockerfile | COPY jobpilot/requirements.txt assumes repo-root build context. | Fixed | Rajesh | None (already met). | Added explicit comment block at the top of the Dockerfile documenting the expected build context (docker build -f jobpilot/Dockerfile .).
35 | 🟢 | Low | 12. Configuration & Deployment | jobpilot/requirements.txt | python-multipart==0.0.9 not used by Flask. | Fixed | Rajesh | None (already met). | Dropped python-multipart from requirements.txt.
55 | 🟢 | Low | 12. Configuration & Deployment | railway.toml | startCommand overrides Dockerfile CMD. | Fixed | Rajesh | None (already met). | Removed startCommand from railway.toml so the Dockerfile CMD is the single source of truth.
68 | 🟢 | Low | 12. Configuration & Deployment | jobpilot/.env.example | APIFY_MODULAR_ACTOR_ID not documented. | Fixed | Rajesh | None (already met). | Added APIFY_MODULAR_ACTOR_ID (and CLAUDE_MODEL) entries with explanatory comments.
30 | 🟠 | High | 13. Testing & CI/CD | repo-wide | No tests, no tests/ directory, no pytest.ini. | WIP | Rajesh | Smoke tests cover /api/health, landing render, demo login, registration validation, and the protected-route guard. Broaden to core/ai_engine.score_ats (mocked Anthropic), core/job_scraper adapters, and route-level resume tests. | Phase 3 added tests/conftest.py, tests/test_auth_smoke.py, pytest.ini, and requirements-dev.txt. 5/5 smoke tests pass locally (python -m pytest -q).
31 | 🟡 | Medium | 13. Testing & CI/CD | repo-wide | No CI/CD configuration. | Fixed | Rajesh | None (already met). | Added .github/workflows/ci.yml: pull-request + push-to-main triggers; matrix python-version: [3.11, 3.12]; jobs run python -m compileall -q jobpilot tests then python -m pytest -q; a separate docker job builds the production image with docker build -f jobpilot/Dockerfile . (Phase 3).
69 | 🟡 | Medium | 14. New — Editor History & Logout Feature (added 2026-05-04) | jobpilot/static/js/app.js | sessionHistory is a top-level mutable global. | Open | — | Wrap app.js in an IIFE or convert to ES modules (needs build tool, see #44/#45); confirm no other globals depend on window.sessionHistory. | Same anti-pattern as #41. Wrap in a module/IIFE; risks redeclaration if app.js is included twice.
70 | 🟢 | Low | 14. New — Editor History & Logout Feature (added 2026-05-04) | jobpilot/static/js/app.js | logout() uses blocking confirm() dialog. | Fixed | Rajesh | None (already met). | Replaced confirm() with a Promise-based appConfirm() modal (markup injected lazily, styled via .app-confirm-* rules in style.css).
71 | 🟢 | Low | 14. New — Editor History & Logout Feature (added 2026-05-04) | jobpilot/static/js/app.js | Two visible **Sign out** buttons exist when the editor is open (topbar + editor status bar). | Fixed | Rajesh | None (already met). | Removed the editor status-bar Sign-out button (and its CSS). Topbar Sign-out is now the single canonical control.
72 | 🟢 | Low | 14. New — Editor History & Logout Feature (added 2026-05-04) | jobpilot/static/js/app.js | Session history is in-memory only; lost on reload, navigation, or logout. | Fixed | Rajesh | None (already met). | Now persisted to sessionStorage (jp_session_history); survives reloads within the browser session, cleared on logout/browser-close.
73 | 🔴 | Critical | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/templates/landing.html | All three landing-page auth handlers (submitAuth, handleGoogleCredential, enterDemoMode) set localStorage.jp_token but never set sessionStorage.jp_session_active='1'. Every successful login/register/Google/demo redirected to /app, where the index.html IIFE immediately wiped the token and bounced back to / — full auth lockout in any fresh browser. | Fixed | Rajesh | None (already met). | Mirrored the session-marker writes from jobpilot/static/js/app.js into all three handlers. Re-tested via Playwright: demo flow now lands on /app with the topbar **Sign out** visible. Memory note recorded under /memories/repo/ so future auth changes are mirrored to both source files.
74 | 🟢 | Low | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/templates/landing.html | Footer **Sign in** / **Get started** anchors had href="#" with no event.preventDefault() — clicking jumped the page to the top before the modal opened. | Fixed | Rajesh | None (already met). | Both onclick handlers now begin with event.preventDefault(); so the modal opens in place.
75 | 🟢 | Low | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/templates/landing.html | Auth-modal "**or continue with**" divider rendered even when no GOOGLE_CLIENT_ID was configured (Google container + fallback button were already hidden), leaving an orphan visual element. | Fixed | Rajesh | None (already met). | Gave the divider id="auth-google-divider" and added it to the same hide branch in initGoogleSignIn() that already hides the Google container/fallback.
76 | 🟢 | Low | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/templates/landing.html | Auth modal still showed the unsubstantiated "Joined by **12,000+** job seekers" stat (mirror of #39, missed in the modal's left rail). | Fixed | Rajesh | None (already met). | Replaced with the verifiable line "Trusted by job seekers everywhere"; avatars retained as decorative.
77 | 🟡 | Medium | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/core/job_scraper.py | _normalize_date had no branch for numeric epoch values, so Arbeitnow's created_at (e.g. "1777906850") leaked into the UI verbatim as a 10-digit raw number. | Fixed | Rajesh | None (already met). | Added an explicit epoch branch (10- or 13-digit numeric strings) that converts to UTC and reuses the same "X hr ago / X days ago / ISO date" formatting as the ISO branch. Verified live: Arbeitnow rows now show "8 hr ago".
78 | 🟡 | Medium | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/static/js/app.js | refreshUsage() called fetch('/api/usage') without authHeaders(), producing a 401 and the visible "Could not load usage data" error in the API Usage panel. | Fixed | Rajesh | None (already met). | Added headers: authHeaders() to the request, matching every other authenticated fetch() in the file.
79 | 🟡 | Medium | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/static/js/app.js | /api/upload-resume upload sent multipart/form-data with no Authorization header — uploads would 401 for the demo user and any other authenticated session. Discovered while wiring up a working UI test. | Fixed | Rajesh | None (already met). | Added Authorization: Bearer <token> to the multipart POST without overriding the implicit boundary (no Content-Type set).
80 | 🟡 | Medium | 14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04) | jobpilot/templates/index.html, jobpilot/templates/landing.html, jobpilot/static/js/app.js | Auth used sessionStorage.jp_session_active as the liveness marker, so any tab/browser close auto-logged-out the user ("still facing login issue"). UX too aggressive: users had to re-auth on every reload-after-close. | Fixed | Rajesh | None (already met). Tunable via the SESSION_TTL_MS / DEMO_SESSION_TTL_MS JS constants in landing.html + app.js. | Replaced the sessionStorage marker with a sliding localStorage.jp_session_expiry (ms-since-epoch). 7 days for real accounts, 24 h for demo accounts. Refreshed on every page load that has a valid token (sliding session). Survives tab close + browser restart; cleared by explicit sign-out, browser **Clear site data**, or the expiry elapsing. Three mirrored helpers (setLoginSession, clearLoginSession, isLoginSessionValid) live in landing.html (auth handlers), app.js (in-app), and the IIFE in index.html — all three keep the same contract. Legacy jp_session_active is purged on every write so old sessions don't linger.
81 | 🟡 | Medium | 14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04) | jobpilot/templates/landing.html, jobpilot/app.py, README.md | Google Sign-In button silently vanished when GOOGLE_CLIENT_ID was unset, with no startup warning or in-product hint. Admins debugging deploys had no signal that the env var was the cause. | Fixed | Rajesh | None (already met). Toggle via ?debug=1 query string on the landing URL. | (a) Startup logger.warning("GOOGLE_CLIENT_ID is not set; Google Sign-In is disabled.") in create_app(). (b) initGoogleSignIn() now branches: production users still see nothing (preserves clean UI), but ?debug=1 renders an inline dashed-border hint reading "Google Sign-In not configured — set GOOGLE_CLIENT_ID". (c) New **Enable Google Sign-In** section in README.md with Cloud Console steps, redirect URI guidance, and the ?debug=1 recipe. The actual rendering code was already correct (#75) — this issue closes the missing diagnostic loop.
82 | 🟢 | Low | 14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04) | jobpilot/static/js/app.js | clearSessionHistory() calls _persistSessionHistory(), but that function is never defined anywhere in app.js — clicking **Clear** in the in-session history panel throws ReferenceError. Likely fallout from the #72 "persist to sessionStorage" change where the helper was inlined and a stale call site remained. | Open | — | Decide whether session history should actually persist to sessionStorage (per the #72 analyst note) or stay in-memory only. Then either (a) implement _persistSessionHistory() (read/write jp_session_history) and matching restore-on-load, or (b) drop the call. Either path needs a single regression test exercising **Clear**. | Pre-existing latent bug; not user-visible until the **Clear** button is clicked, but should be cleaned up alongside the next history-panel touch.
83 | 🔴 | Critical | 14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04) | jobpilot/templates/landing.html | submitAuth() finally block called switchTab(_authTab), which (per switchTab) sets auth-error.style.display = 'none'. Net effect: every failed login/register flashed the real error message for ~0 ms then hid it — user reported "can't login or create account, only demo works." Demo bypassed submitAuth() so it kept working. | Fixed | Rajesh | None (already met). | Replaced the destructive switchTab(_authTab) call with a button-only reset (btn.disabled = false; span.textContent = ...). The error banner now persists until the user retries. Backend (/api/auth/login, /api/auth/register) was healthy throughout — verified end-to-end via PowerShell Invoke-WebRequest (200 OK on register + login).
84 | 🟠 | High | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/ai_engine.py | Default CLAUDE_MODEL is hard-coded to "claude-sonnet-4-6" — not a known Anthropic model SKU (the current released line is claude-sonnet-4-5-*). If CLAUDE_MODEL env var is unset, every AI call (score_ats, tailor_resume, apply_chat_instruction, generate_resume, improve_line, suggest_certifications, answer_screening_question) will 404 from the Anthropic API. Caught by the broad except Exception in each helper, so the user sees a generic "Error: …" string instead of an actionable message. | Open | — | Confirm the intended model id against the current Anthropic models list and either correct the literal or document the env override as mandatory in .env.example + README. Add a one-shot startup ping (e.g. client.models.retrieve(CLAUDE_MODEL)) that logs a clear warning if the SKU is unknown. | Likely a typo for claude-sonnet-4-5. Worth fail-fast at boot rather than silent per-call failures.
85 | 🟠 | High | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/auth_db.py | SECRET_KEY = os.environ.get("JWT_SECRET", "jobpilot-secret-change-in-production") falls back to a hard-coded string at module-import time. Even though app.py validates JWT_SECRET at startup (Issue #1 family), this module-level default means any test harness or one-off python -c "from core.auth_db import create_token; ..." invocation that imports without the env var will silently mint forge-able tokens. Defense-in-depth gap. | Open | — | Drop the fallback — raise RuntimeError("JWT_SECRET must be set") on import if the env var is missing AND we're not under pytest (gate via os.environ.get("PYTEST_CURRENT_TEST")). Pair with a short test asserting that the import fails without the env var in production mode. | Mirrors the well-known "insecure default" anti-pattern; the comment in the literal even says "change-in-production".
86 | 🟠 | High | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | fetch_job_description() calls _is_safe_external_url(url) (which resolves the host via getaddrinfo and checks every returned IP is public) and *then* calls requests.get(url, …) which re-resolves the host independently. A malicious DNS server can return a public IP for the first lookup and a private/loopback IP for the second (classic DNS rebinding TOCTOU), bypassing the SSRF guard added in #63. | Open | — | Pin the resolved IP from the pre-flight check and pass it to requests via a custom HTTPAdapter that overrides DNS, OR use a connection-level adapter that re-validates the resolved IP on each socket connect. Add a regression test using a custom resolver that flips the answer between calls. | High-impact, low-likelihood — exploitation requires the attacker to control the URL *and* DNS for the host; still worth closing because the guard is otherwise solid.
87 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | _SEARCH_CACHE: dict[tuple, tuple[float, list[dict]]] has no eviction. Every distinct (title, location, seniority, date_posted) tuple grows the dict forever; with frequent users searching varied roles the dict will grow unbounded over the process lifetime. Each entry can hold ~hundreds of job dicts (multi-KB each). | Open | — | Replace with functools.lru_cache(maxsize=128) on a thin wrapper, or add an explicit LRU sweep that drops entries with (now - ts) > _SEARCH_CACHE_TTL_SEC whenever the dict exceeds N entries. | Same pattern as #22 (in-memory usage counter) — fine for single-user dev, dangerous on Railway where the worker stays warm for hours.
88 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | All five search_apify_* functions (linkedin, indeed, glassdoor, ziprecruiter, modular) call _SESSION.post(...) against the module-level singleton, while every other scraper goes through the per-thread _session() introduced in Issue #25. Under ThreadPoolExecutor parallel fan-out from search_all_platforms, this re-opens the thread-safety hole #25 closed (mutating Session.headers mid-flight, shared connection pool contention). | Open | — | Replace _SESSION.post(...) with _session().post(...) in all five Apify functions. Audit the file with grep _SESSION\. to make sure no other call sites slipped through. | Mechanical fix; one-line per function. The discovery helper _discover_apify_actors is single-threaded at startup, so it can keep using _SESSION.
89 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | search_all_platforms fans 6 scrapers into a ThreadPoolExecutor and waits via as_completed(futures) with no overall deadline. The Apify run-sync-get-dataset-items calls have a 130-second per-request timeout. A single slow Apify actor stalls the entire /api/jobs/search response for 130s, with the user seeing only a spinning loader. | Open | — | Wrap as_completed in a budget — e.g. for fut in as_completed(futures, timeout=45): … and treat unfinished futures as failed sources (cancel + log). Surface a partial-results banner in the UI when sources timed out. | Pairs naturally with a circuit-breaker around Apify (per-actor failure counter that skips the actor for N seconds after K consecutive timeouts).
90 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/ai_engine.py, jobpilot/core/ai_engine.py, jobpilot/core/ai_engine.py | tailor_resume, apply_chat_instruction, generate_resume, and answer_screening_question all silently truncate inputs (resume_text[:6000], job_description[:3000], description[:2000], etc.) without surfacing any warning to the caller. Only score_ats reports truncation_warning. Long resumes / JDs lose tail content (often the most recent role) with no user feedback. | Open | — | Promote the truncation_warning pattern from score_ats into a shared helper, return it in every result dict, and surface a small banner in the UI when present. Limits should remain env-overridable (existing pattern). | Affects user trust: "why didn't AI mention my latest job?" — it never saw it.
91 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_reader.py | save_tailored_pdf swallows every WeasyPrint exception and silently falls back to the ReportLab path. The two paths produce visibly different PDFs (different fonts, spacing, no teal accent). End-users hitting a WeasyPrint misconfig (missing system libs, font failure) get a degraded PDF with no notice and no trail beyond a logger.warning. | Open | — | Either (a) propagate the WeasyPrint failure to the route layer and return a 502 with a clear message, or (b) include a one-line note in the response payload (pdf_renderer: "reportlab-fallback") and surface it in the UI when downloading. Add a smoke test that asserts WeasyPrint actually ran in the happy path. | Currently masks production-impacting deploy issues (e.g. Railway image missing libpango).
92 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/auth_db.py | create_user(email, password) does no validation at the DB layer — it lower()s the email and inserts whatever is provided. All format/length/strength enforcement happens in jobpilot/routes/auth.py; any other future caller (admin script, batch import, future API) bypasses the checks. | Open | — | Add minimal defense-in-depth in create_user: regex on email shape, len(password) >= 8 (or read from env), and reject obviously invalid inputs with ValueError. Do *not* duplicate the route-layer messages — those stay user-facing; this is the safety net. | Pairs naturally with #2 (input validation) once that work starts.
93 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | _get_apify_actor_ids() makes a live HTTP call to api.apify.com/v2/acts on first invocation. _APIFY_ACTORS_CACHE is populated only on success — there is no negative cache, so every job search during an Apify outage re-issues the discovery call (and pays its full 30s timeout). | Open | — | Cache *both* success and failure for at least 5 minutes. Even a _APIFY_ACTORS_CACHE = DEFAULT_APIFY_ACTORS.copy() populated on failure (timestamped) would prevent the per-request retry storm. | Symptom appears as "every search is suddenly slow" — hard to diagnose without log scraping.
94 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_reader.py | read_resume(filename) builds the path as RESUMES_DIR / filename with no traversal sanitization. If any future caller passes a user-controlled filename containing .., the function will read arbitrary files inside the container. The route layer (jobpilot/routes/resume.py) currently sanitizes, but the helper is a footgun for any new caller. | Open | — | Reuse the existing _safe_stem() helper at the top of read_resume (or a parallel _safe_in_path()) and reject anything that resolves outside RESUMES_DIR. Mirror the pattern in _safe_out_path (resolve + startswith check). | Defense-in-depth — same hardening shape as #67/#65.
95 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/ai_engine.py | Dead-code typo: parts = after_later = after_label.split("✅ Change Log:", 1). The variable after_later is never read again — looks like a misspelling of after_label that the author meant to drop. Confusing on review and trips static analysis. | Open | — | Delete the after_later = chained assignment so the line reads parts = after_label.split("✅ Change Log:", 1). | Pure cleanup; no behavior change.
96 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | _get() always sleeps random.uniform(0.2, 0.6) before issuing the request, even when called from concurrent worker threads in search_all_platforms. With ~6 sources × up to 4 paginated requests each, this adds ~5–15 seconds of pure sleep per search wall-clock budget. | Open | — | Drop the unconditional sleep. If rate-limit jitter is needed, gate it per-host (only the slow sources — Adzuna and JSearch) and give it a tighter upper bound (≤200 ms). | Easy win for perceived search speed.
97 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_normalizer.py | normalize_job_title only matches whole-string lookups in JOB_TITLE_SYNONYMS. The dict has entries like "sr.", "sr ", "jr." that can never match, because no real title equals exactly "sr ". Same for the prefix entries — normalize_job_title("Sr Engineer") returns the input unchanged. | Open | — | Either (a) tokenize the title and apply prefix/suffix replacements (re.sub(r'\bsr\.?\b', 'senior', t, flags=I)), or (b) drop the dead dict entries and document that this helper is exact-match only. Pick one and add a unit test for "Sr Data Engineer". | Low-impact today (no caller uses this in production paths) but the dict is misleading on first read.
98 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/auth_db.py | decode_token() does payload["sub"] directly, raising KeyError if a JWT was signed with our secret but lacks the sub claim. The function's docstring promises only jwt.PyJWTError on failure, so callers who narrow their except will crash with an unhandled KeyError. | Open | — | Use payload.get("sub") and raise jwt.InvalidTokenError("sub claim missing") if None. Update the docstring or add a regression test. | Pure contract bug; trivial fix.
99 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_reader.py | TODO / refactor: save_tailored_pdf is ~270 lines including a near-duplicate _build_story_with_scale that re-parses content from scratch with parallel paragraph styles. Maintenance hazard — any new section type must be added in two places. | Open | — | Extract the line-walking parser into a single function that yields (kind, text) tuples, then have both the unscaled and scaled builders consume the same iterator and apply scale only at style construction. No behavior change expected. | Refactor candidate for the next time this file is opened for a real fix.
100 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_reader.py | TODO / refactor: read_resume_bytes (added per Issue #67) and read_resume duplicate the PDF/DOCX extraction logic — the on-disk path opens files, the in-memory path wraps BytesIO, but the parser bodies are otherwise identical. | Open | — | Have read_resume(filename) open the file into bytes and delegate to read_resume_bytes(content, ext). Keep the txt fast-path. Adds one extra read for txt and zero for pdf/docx (which already buffer in memory). | Closes the rest of #67's deduplication intent.

## 1. Security
1. Security
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
1 | 🔴 | Critical | 1. Security | jobpilot/app.py | Hardcoded fallback for FLASK_SECRET (jobpilot-flask-secret). | Open | — | FLASK_SECRET env var present in Railway + .env; startup guard that aborts on missing/short value; smoke test confirming app.secret_key is not the literal fallback. | Session forgery is trivial if env var is unset; fail-fast on missing secret.
2 | 🔴 | Critical | 1. Security | jobpilot/core/auth_db.py | Hardcoded fallback for JWT_SECRET. | Open | — | JWT_SECRET env var present in Railway + .env; fail-fast guard in auth_db._get_secret(); rotate any tokens issued under the dev fallback. | Same risk as #1 for token forgery; require the env var or abort startup.
4 | 🟠 | High | 1. Security | jobpilot/app.py | Auth guard uses path.startswith("/static") (no trailing slash). | Open | — | One-line change to "/static/"; regression test hitting /staticXYZ and /static/... to assert 401 vs. 200. | Allows /staticXYZ to bypass auth; change to /static/.
3 | 🟠 | High | 1. Security | jobpilot/core/auth_db.py | passlib configured for pbkdf2_sha256, not bcrypt as commented. | Open | — | Decision: keep pbkdf2_sha256 (update docs) **or** add bcrypt/argon2-cffi to requirements.txt and migrate existing hashes via CryptContext(schemes=[...], deprecated="auto"). | Align code with intent and requirements.txt; bcrypt or argon2 is preferred.
63 | 🟡 | Medium | 1. Security | jobpilot/core/job_scraper.py | fetch_job_description accepts arbitrary URLs (SSRF). | Fixed | Rajesh | None (already met). | New _is_safe_external_url(url) allow-list: only http(s), host resolved with getaddrinfo, every returned IP must be public-routable (rejects is_private/is_loopback/is_link_local/is_multicast/is_reserved/is_unspecified plus the CGNAT block 100.64.0.0/10). Outbound request also runs with allow_redirects=False so a 30x to an internal host can't bypass the pre-flight check. Severity bumped to 🟠 to reflect the original metadata-endpoint exposure now closed.
6 | 🟡 | Medium | 1. Security | jobpilot/routes/resume.py | Download endpoint relies on user-supplied filename. | Fixed | Rajesh | None (already met). | Sanitization is now explicit at the route boundary — safe_stem = re.sub(r"[^A-Za-z0-9_\-]", "_", Path(os.path.basename(raw_name)).stem) or "resume"; save_tailored_* then resolves under GENERATED_DIR and raises ValueError on traversal.
5 | 🟡 | Medium | 1. Security | jobpilot/app.py | JWT and decoder imports inside before_request. | Fixed | Rajesh | None (already met). | jwt as pyjwt and decode_token are now imported at module scope so each request skips the import-cache lookup.
7 | 🟡 | Medium | 1. Security | jobpilot/routes/auth.py | Google-OAuth users get random hex password. | Won't Fix | — | **Requirements (must agree before reopening):** (a) schema migration adding auth_provider column to users (paired with #23 Postgres migration), (b) backfill script tagging existing OAuth rows, (c) /api/auth/login change rejecting password login when auth_provider != 'local', (d) UI copy explaining the rejection on the login form. | Deferred until the Postgres migration (#23) lands so we don't write a SQLite-only schema change.
8 | 🟢 | Low | 1. Security | jobpilot/templates/landing.html | Terms / Privacy links resolve to #. | Fixed | Rajesh | None (already met). Replace placeholder body with real legal copy before public launch. | Replaced with real /terms and /privacy routes serving placeholder pages in jobpilot/app.py.

## 2. Data Validation & Input Hard
2. Data Validation & Input Hardening
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
52 | 🟡 | Medium | 2. Data Validation & Input Hardening | jobpilot/routes/resume.py | Resume upload reads file with no size check. | Fixed | Rajesh | None (already met). Tunable via RESUME_MAX_BYTES. | Added MAX_RESUME_BYTES (default 5 MB, env-overridable via RESUME_MAX_BYTES); upload returns HTTP 413 with a friendly message when exceeded.
53 | 🟡 | Medium | 2. Data Validation & Input Hardening | jobpilot/routes/resume.py | generate-resume description has no length cap. | Fixed | Rajesh | None (already met). Tunable via RESUME_DESCRIPTION_MAX_CHARS. | Added MAX_DESCRIPTION_CHARS (default 8000, env-overridable via RESUME_DESCRIPTION_MAX_CHARS); endpoint short-circuits with HTTP 413 before the Claude call.
51 | 🟡 | Medium | 2. Data Validation & Input Hardening | jobpilot/routes/auth.py | Email validated only by presence of @. | Fixed | Rajesh | None (already met). | Replaced the "@" in email check with an RFC-5322-lite regex (_EMAIL_RE) plus a 254-char length cap in _is_valid_email().
65 | 🟡 | Medium | 2. Data Validation & Input Hardening | jobpilot/static/js/app.js | Job title interpolated into innerHTML unsanitized in showSearching. | Fixed | Rajesh | None (already met). | Title is now wrapped with escHtml(title) before injection, closing the reflected-XSS surface.
66 | 🟢 | Low | 2. Data Validation & Input Hardening | jobpilot/core/ai_engine.py | Resume/JD silently truncated at 6000/3000 chars. | Fixed | Rajesh | None (already met). UI surface for the warning is a future polish item. | score_ats() now returns truncation_warning in its result dict whenever input was clipped; UI can surface it.

## 3. Authentication & Authorizati
3. Authentication & Authorization
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
37 | 🟡 | Medium | 3. Authentication & Authorization | jobpilot/templates/index.html | Auth check is a JS localStorage redirect. | Won't Fix | — | **Requirements:** (a) Cookie-auth design with Secure / HttpOnly / SameSite=Lax defaults, (b) CSRF strategy (double-submit cookie or origin check), (c) refresh-token endpoint, (d) frontend rewrite of every authHeaders() call site, (e) backend @app.get("/app") server-side guard. Pairs with #37/#73 client-side hardening already done. | Deferred — multi-week security redesign, not a drive-by edit.

## 4. Error Handling & Observabili
4. Error Handling & Observability
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
19 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/routes/resume.py | except Exception: pass after pypdf read. | Fixed | Rajesh | None (already met). | Replaced silent pass with logger.warning("pypdf extraction failed (%s); falling back to pdfplumber", e) so failures are diagnosable while the fallback still runs.
20 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/job_scraper.py | 39 broad except Exception blocks across the codebase. | Won't Fix | — | **Requirements (must agree before reopening):** (a) the pytest baseline (#30) must be broader than the current smoke tests — needs unit coverage of every adapter so behavior changes are caught, (b) per-module exception inventory (grep + manual triage), (c) agreed error-class taxonomy (requests.RequestException, KeyError, json.JSONDecodeError, etc.), (d) replace bare excepts in priority order with exc_info=True logging. | Deliberately deferred per AGENTS.md §4 — careful semantic review needed; not a drive-by edit.
21 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/resume_reader.py | render_to_pdf returns silently on page-count failure. | Fixed | Rajesh | None (already met). | Failure now flows through logging.getLogger("jobpilot").warning(...) (lands in the configured RotatingFileHandler) before the ReportLab fallback.
12 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/ai_engine.py | print() used for errors (7+ sites). | Fixed | Rajesh | None (already met). | Module-scope logger = logging.getLogger("jobpilot") added; all 7 print(f"[…] error: {e}") sites swapped to logger.warning("[…] error: %s", e). Output now flows through the configured RotatingFileHandler in app.py (Phase 3).
13 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/job_scraper.py | ~30 print() calls used for diagnostics. | Fixed | Rajesh | None (already met). | All 42 print() sites migrated to logger.info (status / counts) or logger.warning (errors / Failed/Error strings) keeping the per-source [adapter] prefixes intact (Phase 3).
14 | 🟡 | Medium | 4. Error Handling & Observability | jobpilot/core/resume_reader.py | print() used in 6 error paths. | Fixed | Rajesh | None (already met). | Module logger added; print() calls in read_resume, save_tailored_pdf, and save_tailored_docx swapped to logger.warning(..., exc_info=True) where the previous code also called traceback.print_exc() (Phase 3).

## 5. Architecture & Scalability
5. Architecture & Scalability
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
23 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/core/auth_db.py | SQLite used as production user store. | Won't Fix | — | **Requirements (must agree before reopening):** (a) provision Postgres on Railway (plan upgrade), (b) add psycopg[binary] (or asyncpg), (c) abstract auth_db behind a connection-pool layer, (d) write SQLite→Postgres migration script, (e) add DATABASE_URL env var, (f) update tests to spin up a temporary Postgres (or use pytest-postgresql). | Deferred infra change — not a drive-by edit (AGENTS.md §4).
24 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/core/auth_db.py | New SQLite connection per call; no pooling. | Won't Fix | — | **Requirements:** Paired with #23 — same Postgres migration scope. Interim thread-local sqlite3.Connection rejected because it would mask the bigger concurrency problem. | Deferred until #23 lands.
22 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/app.py | Usage counters held in module-level dict. | Won't Fix | — | **Requirements:** Persistent backing store — either a usage_counters table (paired with #23) or Redis (redis-py); decision on whether counters are per-user or global; pricing-tier coupling (free vs paid). | Deferred until the persistence story (#23) is settled.
25 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/core/job_scraper.py | Global requests.Session with mutable headers. | Fixed | Rajesh | None (already met). | Replaced module-level _SESSION with _session() returning a per-thread requests.Session from threading.local() (_SESSION_TLS). Each session is built via _build_session(), mounted with the new retry adapter (#61). Backwards-compat _SESSION alias retained for any external callers (Phase 3).
67 | 🟡 | Medium | 5. Architecture & Scalability | jobpilot/routes/resume.py | PDF/DOCX/TXT parsing duplicated vs. resume_reader.read_resume. | Fixed | Rajesh | None (already met). | Introduced read_resume_bytes(content, ext) in core/resume_reader.py; the upload route now delegates so the two code paths can no longer drift apart. Same logger and pdfplumber-fallback contract as the disk path (Phase 3).
26 | 🟢 | Low | 5. Architecture & Scalability | jobpilot/core/job_scraper.py | _get_apify_actor_ids() HTTP call at import time. | Fixed | Rajesh | None (already met). | Replaced eager call with _LazyApifyActors proxy + get_apify_actors(); HTTP now happens on first use. Existing APIFY_ACTORS[...] lookups continue to work.

## 6. Performance & Cost
6. Performance & Cost
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
27 | 🟡 | Medium | 6. Performance & Cost | jobpilot/core/ai_engine.py | No caching for Claude calls. | Won't Fix | — | **Requirements:** (a) cache backend decision (in-process LRU is fine for single-instance deploys but breaks under multi-worker WSGI/Railway scale-out — likely needs Redis once #22 lands), (b) prompt-versioning scheme so prompt edits invalidate entries, (c) per-call-type TTL (ATS=15 min, tailor=never — each result is per-job), (d) per-user quota check before serving stale entries. | Caching the wrong call would silently serve stale answers; deferred until backend + versioning are agreed.
11 | 🟡 | Medium | 6. Performance & Cost | jobpilot/core/ai_engine.py | New Anthropic client per call. | Fixed | Rajesh | None (already met). | _client() now memoises a single anthropic.Anthropic instance in module-level _CLIENT; subsequent calls reuse the existing HTTP connection pool.
29 | 🟡 | Medium | 6. Performance & Cost | jobpilot/core/resume_reader.py | PDF auto-fit rebuilds the doc up to 6 times. | Fixed | Rajesh | None (already met). | Replaced linear [1.0, 0.95, ..., 0.75] scan with a fast-path full-scale build then a 6-iteration binary search on [0.75, 1.0]. Worst-case build count unchanged; best-case (most resumes fit at scale 1.0) drops from 1 build to 1, and medium-length resumes converge to the largest fitting scale rather than the next coarse step (Phase 3).
28 | 🟢 | Low | 6. Performance & Cost | jobpilot/core/job_scraper.py | search_all_platforms results not cached. | Fixed | Rajesh | None (already met). | Added a 90-second in-memory TTL cache keyed on (title, location, seniority, date_posted). Repeat clicks now skip the API fan-out entirely.

## 7. Resilience & External Integr
7. Resilience & External Integration
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
61 | 🟡 | Medium | 7. Resilience & External Integration | jobpilot/core/job_scraper.py | _get() has no retry logic. | Fixed | Rajesh | None (already met). | _build_session() now mounts an HTTPAdapter with urllib3.util.Retry(total=3, backoff_factor=0.4, status_forcelist=(429, 500, 502, 503, 504), allowed_methods=frozenset(("GET", "HEAD")), raise_on_status=False). Idempotent-only retries; per-host budget capped at 3 attempts; pool_maxsize=8 (Phase 3).
60 | 🟡 | Medium | 7. Resilience & External Integration | jobpilot/core/job_scraper.py | Per-request 0.2–0.6 s sleep insufficient under thread pool. | Won't Fix | — | **Requirements:** (a) per-provider rate-limit decision (Apify/Adzuna/JSearch each publish different limits), (b) library choice (pyrate-limiter vs hand-rolled threading.Semaphore per host), (c) coordination with the #61 retry budget so we don't double-throttle, (d) optional per-user fairness layer once #22 lands. | Deferred until provider-specific limits are catalogued.

## 8. Code Quality & Maintainabili
8. Code Quality & Maintainability
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
9 | 🔴 | Critical | 8. Code Quality & Maintainability | jobpilot/core/ai_engine.py | parts = after_later = after_label.split(...) — after_later unused. | Open | — | Read the surrounding apply_chat_instruction parser to confirm intent; targeted unit test for the chat-instruction split before the cleanup; small surgical edit. | Latent bug; remove the chained assignment.
17 | 🟠 | High | 8. Code Quality & Maintainability | jobpilot/core/resume_reader.py | ~80-line PDF parsing block duplicated inside _build_story_with_scale. | Open | — | Extract a _parse_resume_to_story(content, styles) helper; golden-output regression tests for at least 3 sample resumes (since visual layout is hard to lint). | Extract a single parser function; current state guarantees drift.
18 | 🟡 | Medium | 8. Code Quality & Maintainability | jobpilot/core/resume_reader.py | re re-imported inside save_tailored_pdf. | Fixed | Rajesh | None (already met). | Removed the redundant import re (already imported at module scope on line 6); only the local import io for the ReportLab buffer remains, with an explanatory comment.
10 | 🟡 | Medium | 8. Code Quality & Maintainability | jobpilot/core/ai_engine.py | load_dotenv called both here and in app.py. | Fixed | Rajesh | None (already met). | Removed the redundant load_dotenv call from core/ai_engine.py; app.py is now the single authoritative env loader (documented inline in both files).
64 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/ai_engine.py | Claude model name hardcoded (claude-sonnet-4-6). | Fixed | Rajesh | None (already met). Override with CLAUDE_MODEL env var. | Extracted to module-level CLAUDE_MODEL constant, env-overridable via CLAUDE_MODEL. Both _call() and the chat client now read it.
15 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/resume_normalizer.py | "professional experience" key duplicated in SECTION_SYNONYMS. | Fixed | Rajesh | None (already met). | Removed the duplicate dict key.
16 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/resume_reader.py | Local sp(base) defined but never called. | Fixed | Rajesh | None (already met). | Dead helper removed from _build_story_with_scale.
62 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/resume_normalizer.py | normalize_company, normalize_job_title, normalize_degree unreferenced. | Fixed | Rajesh | None (already met). | Kept (intended public normalization API) and prefixed with a documentation block declaring them public so they're not flagged again.
50 | 🟢 | Low | 8. Code Quality & Maintainability | jobpilot/core/auth_db.py | Module docstring says auth.py. | Fixed | Rajesh | None (already met). | Docstring now reads auth_db.py and reflects the actual pbkdf2_sha256 algorithm.

## 9. API Design
9. API Design
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
46 | 🟡 | Medium | 9. API Design | jobpilot/routes/jobs.py | jsearch_requests / adzuna_requests incremented unconditionally. | Fixed | Rajesh | None (already met). | Increments are now gated on RAPIDAPI_KEY / (ADZUNA_APP_ID + ADZUNA_APP_KEY) being present, so the usage dashboard doesn't inflate counts when those integrations are disabled.
47 | 🟢 | Low | 9. API Design | jobpilot/routes/resume.py | improve_line does not increment claude_calls. | Fixed | Rajesh | None (already met). | Counter now incremented before delegating to improve_line().
48 | 🟢 | Low | 9. API Design | jobpilot/routes/resume.py | suggest_certs does not increment claude_calls. | Fixed | Rajesh | None (already met). | Counter incremented before suggest_certifications() call.
49 | 🟢 | Low | 9. API Design | jobpilot/routes/resume.py | answer endpoint does not increment claude_calls. | Fixed | Rajesh | None (already met). | Counter incremented before answer_screening_question() call.

## 10. Frontend
10. Frontend
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
41 | 🟡 | Medium | 10. Frontend | jobpilot/static/js/app.js | _authTab declared in both app.js and landing.html. | Fixed | Rajesh | None (already met). | Removed the duplicate _authTab declaration from app.js (auth UI lives only in landing.html). Added a comment block at the top of the auth section in app.js explicitly documenting the contract so the two sources can't accidentally re-fork (Phase 3).
42 | 🟡 | Medium | 10. Frontend | jobpilot/static/js/app.js | switchAuthTab references DOM IDs that no longer exist. | Fixed | Rajesh | None (already met). | Replaced switchAuthTab and the dead submitAuth body with no-op stubs that document the dead-code path. Stubs are safe against any stale cached HTML still binding onclick="switchAuthTab(...)" (Phase 3).
43 | 🟡 | Medium | 10. Frontend | jobpilot/static/js/app.js | Theme keys (light-pro/dark-pro) mismatch HTML options (light/dark). | Fixed | Rajesh | None (already met). | Added normalizeThemeKey() so persisted light-pro/dark-pro values from older builds are migrated to the canonical light/dark on first load. applyTheme() now writes the normalized key to <html data-theme="…"> and localStorage, matching style.css and base.html (Phase 3).
44 | 🟢 | Low | 10. Frontend | jobpilot/static/css/style.css | Single 80 KB CSS file. | Won't Fix | — | Build tool (esbuild / Vite / Parcel); CSS module split plan; CI step to bundle. Deferred until tooling lands. | Tracked separately as part of the Foundations sprint (full module split). Not a single-PR low-priority fix; deferred with this rationale.
45 | 🟢 | Low | 10. Frontend | jobpilot/static/js/app.js | Single 85 KB JS file. | Won't Fix | — | Same as #44 — needs a bundler before splitting. | Same as #44. Modularization will be planned alongside a build tool (esbuild/Vite) introduction.
36 | 🟢 | Low | 10. Frontend | jobpilot/templates/base.html | Only Inter web font preloaded. | Fixed | Rajesh | None (already met). | Added a comment in base.html explicitly documenting that PDF generation falls back to Times/system fonts and Inter is the only web font.
38 | 🟢 | Low | 10. Frontend | jobpilot/templates/landing.html | Hardcoded copyright © 2025. | Fixed | Rajesh | None (already met). | Footer now uses <span id="ln-footer-year"> populated by JS at load time.
39 | 🟢 | Low | 10. Frontend | jobpilot/templates/landing.html | Marketing stats (2.4M+/98%/12K+) appear unsubstantiated. | Fixed | Rajesh | None (already met). | Removed unsubstantiated stat cards and the "Search 2.4M+ US jobs live" hero copy. Kept verifiable stats (6 boards, 3× faster).
40 | 🟢 | Low | 10. Frontend | jobpilot/static/js/app.js | const API = ""; (same-origin only). | Fixed | Rajesh | None (already met). Override with window.JOBPILOT_API_BASE. | API now reads window.JOBPILOT_API_BASE if set; falls back to same-origin. Documented inline.

## 11. Accessibility & SEO
11. Accessibility & SEO
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
56 | 🟡 | Medium | 11. Accessibility & SEO | jobpilot/templates/index.html | Interactive elements lack ARIA roles/labels. | Won't Fix | — | **Requirements:** (a) full WCAG 2.1 AA audit baseline via axe-core or Lighthouse CI, (b) per-control inventory with aria-label/aria-expanded/focus-management defects, (c) dedicated a11y sprint (not a drive-by edit). | Deferred until a11y sprint is scheduled.
57 | 🟢 | Low | 11. Accessibility & SEO | jobpilot/templates/landing.html | Decorative/feature SVGs lack accessible names. | Fixed | Rajesh | None (already met). | Inline init script now applies aria-hidden="true" + focusable="false" to every <svg> inside .landing-root that has no explicit aria-label/role.
58 | 🟢 | Low | 11. Accessibility & SEO | jobpilot/templates/base.html | No <meta name="description">. | Fixed | Rajesh | None (already met). | Added a meta_description Jinja block in base.html with a sensible default.
59 | 🟢 | Low | 11. Accessibility & SEO | jobpilot/templates/base.html | No Open Graph / Twitter Card tags. | Fixed | Rajesh | None (already met). | Added og:type/title/description/site_name and twitter:card/title/description blocks in base.html.

## 12. Configuration & Deployment
12. Configuration & Deployment
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
54 | 🟡 | Medium | 12. Configuration & Deployment | jobpilot/Dockerfile | Container runs as root. | Fixed | Rajesh | None (already met). | Added a system appuser (uid 1001), chown'd /app, and dropped to USER appuser before CMD.
32 | 🟡 | Medium | 12. Configuration & Deployment | jobpilot/.env.example | FLASK_SECRET missing from .env.example. | Fixed | Rajesh | None (already met). Pairs with still-open #1 fail-fast guard. | FLASK_SECRET= is now present in .env.example so first-time deploys see the required env var; the still-open #1 will close the loop with a startup guard that aborts on missing/short secret.
33 | 🟡 | Medium | 12. Configuration & Deployment | jobpilot/.gitignore | generated/ rule is commented out. | Fixed | Rajesh | None (already met). | Verified the working .gitignore already enforces jobpilot/generated/, jobpilot/logs/, and jobpilot/resumes/ — the original line ref pre-dated that change. No further action required.
34 | 🟢 | Low | 12. Configuration & Deployment | jobpilot/Dockerfile | COPY jobpilot/requirements.txt assumes repo-root build context. | Fixed | Rajesh | None (already met). | Added explicit comment block at the top of the Dockerfile documenting the expected build context (docker build -f jobpilot/Dockerfile .).
35 | 🟢 | Low | 12. Configuration & Deployment | jobpilot/requirements.txt | python-multipart==0.0.9 not used by Flask. | Fixed | Rajesh | None (already met). | Dropped python-multipart from requirements.txt.
55 | 🟢 | Low | 12. Configuration & Deployment | railway.toml | startCommand overrides Dockerfile CMD. | Fixed | Rajesh | None (already met). | Removed startCommand from railway.toml so the Dockerfile CMD is the single source of truth.
68 | 🟢 | Low | 12. Configuration & Deployment | jobpilot/.env.example | APIFY_MODULAR_ACTOR_ID not documented. | Fixed | Rajesh | None (already met). | Added APIFY_MODULAR_ACTOR_ID (and CLAUDE_MODEL) entries with explanatory comments.

## 13. Testing & CICD
13. Testing & CI/CD
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
30 | 🟠 | High | 13. Testing & CI/CD | repo-wide | No tests, no tests/ directory, no pytest.ini. | WIP | Rajesh | Smoke tests cover /api/health, landing render, demo login, registration validation, and the protected-route guard. Broaden to core/ai_engine.score_ats (mocked Anthropic), core/job_scraper adapters, and route-level resume tests. | Phase 3 added tests/conftest.py, tests/test_auth_smoke.py, pytest.ini, and requirements-dev.txt. 5/5 smoke tests pass locally (python -m pytest -q).
31 | 🟡 | Medium | 13. Testing & CI/CD | repo-wide | No CI/CD configuration. | Fixed | Rajesh | None (already met). | Added .github/workflows/ci.yml: pull-request + push-to-main triggers; matrix python-version: [3.11, 3.12]; jobs run python -m compileall -q jobpilot tests then python -m pytest -q; a separate docker job builds the production image with docker build -f jobpilot/Dockerfile . (Phase 3).

## 14. New — Editor History & Logo
14. New — Editor History & Logout Feature (added 2026-05-04)
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
69 | 🟡 | Medium | 14. New — Editor History & Logout Feature (added 2026-05-04) | jobpilot/static/js/app.js | sessionHistory is a top-level mutable global. | Open | — | Wrap app.js in an IIFE or convert to ES modules (needs build tool, see #44/#45); confirm no other globals depend on window.sessionHistory. | Same anti-pattern as #41. Wrap in a module/IIFE; risks redeclaration if app.js is included twice.
70 | 🟢 | Low | 14. New — Editor History & Logout Feature (added 2026-05-04) | jobpilot/static/js/app.js | logout() uses blocking confirm() dialog. | Fixed | Rajesh | None (already met). | Replaced confirm() with a Promise-based appConfirm() modal (markup injected lazily, styled via .app-confirm-* rules in style.css).
71 | 🟢 | Low | 14. New — Editor History & Logout Feature (added 2026-05-04) | jobpilot/static/js/app.js | Two visible **Sign out** buttons exist when the editor is open (topbar + editor status bar). | Fixed | Rajesh | None (already met). | Removed the editor status-bar Sign-out button (and its CSS). Topbar Sign-out is now the single canonical control.
72 | 🟢 | Low | 14. New — Editor History & Logout Feature (added 2026-05-04) | jobpilot/static/js/app.js | Session history is in-memory only; lost on reload, navigation, or logout. | Fixed | Rajesh | None (already met). | Now persisted to sessionStorage (jp_session_history); survives reloads within the browser session, cleared on logout/browser-close.

## 14b. New — Live Playwright UI S
14b. New — Live Playwright UI Sprint (added 2026-05-04)
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
73 | 🔴 | Critical | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/templates/landing.html | All three landing-page auth handlers (submitAuth, handleGoogleCredential, enterDemoMode) set localStorage.jp_token but never set sessionStorage.jp_session_active='1'. Every successful login/register/Google/demo redirected to /app, where the index.html IIFE immediately wiped the token and bounced back to / — full auth lockout in any fresh browser. | Fixed | Rajesh | None (already met). | Mirrored the session-marker writes from jobpilot/static/js/app.js into all three handlers. Re-tested via Playwright: demo flow now lands on /app with the topbar **Sign out** visible. Memory note recorded under /memories/repo/ so future auth changes are mirrored to both source files.
74 | 🟢 | Low | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/templates/landing.html | Footer **Sign in** / **Get started** anchors had href="#" with no event.preventDefault() — clicking jumped the page to the top before the modal opened. | Fixed | Rajesh | None (already met). | Both onclick handlers now begin with event.preventDefault(); so the modal opens in place.
75 | 🟢 | Low | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/templates/landing.html | Auth-modal "**or continue with**" divider rendered even when no GOOGLE_CLIENT_ID was configured (Google container + fallback button were already hidden), leaving an orphan visual element. | Fixed | Rajesh | None (already met). | Gave the divider id="auth-google-divider" and added it to the same hide branch in initGoogleSignIn() that already hides the Google container/fallback.
76 | 🟢 | Low | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/templates/landing.html | Auth modal still showed the unsubstantiated "Joined by **12,000+** job seekers" stat (mirror of #39, missed in the modal's left rail). | Fixed | Rajesh | None (already met). | Replaced with the verifiable line "Trusted by job seekers everywhere"; avatars retained as decorative.
77 | 🟡 | Medium | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/core/job_scraper.py | _normalize_date had no branch for numeric epoch values, so Arbeitnow's created_at (e.g. "1777906850") leaked into the UI verbatim as a 10-digit raw number. | Fixed | Rajesh | None (already met). | Added an explicit epoch branch (10- or 13-digit numeric strings) that converts to UTC and reuses the same "X hr ago / X days ago / ISO date" formatting as the ISO branch. Verified live: Arbeitnow rows now show "8 hr ago".
78 | 🟡 | Medium | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/static/js/app.js | refreshUsage() called fetch('/api/usage') without authHeaders(), producing a 401 and the visible "Could not load usage data" error in the API Usage panel. | Fixed | Rajesh | None (already met). | Added headers: authHeaders() to the request, matching every other authenticated fetch() in the file.
79 | 🟡 | Medium | 14b. New — Live Playwright UI Sprint (added 2026-05-04) | jobpilot/static/js/app.js | /api/upload-resume upload sent multipart/form-data with no Authorization header — uploads would 401 for the demo user and any other authenticated session. Discovered while wiring up a working UI test. | Fixed | Rajesh | None (already met). | Added Authorization: Bearer <token> to the multipart POST without overriding the implicit boundary (no Content-Type set).

## 14c. New — TTL Session + Google
14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04)
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
80 | 🟡 | Medium | 14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04) | jobpilot/templates/index.html, jobpilot/templates/landing.html, jobpilot/static/js/app.js | Auth used sessionStorage.jp_session_active as the liveness marker, so any tab/browser close auto-logged-out the user ("still facing login issue"). UX too aggressive: users had to re-auth on every reload-after-close. | Fixed | Rajesh | None (already met). Tunable via the SESSION_TTL_MS / DEMO_SESSION_TTL_MS JS constants in landing.html + app.js. | Replaced the sessionStorage marker with a sliding localStorage.jp_session_expiry (ms-since-epoch). 7 days for real accounts, 24 h for demo accounts. Refreshed on every page load that has a valid token (sliding session). Survives tab close + browser restart; cleared by explicit sign-out, browser **Clear site data**, or the expiry elapsing. Three mirrored helpers (setLoginSession, clearLoginSession, isLoginSessionValid) live in landing.html (auth handlers), app.js (in-app), and the IIFE in index.html — all three keep the same contract. Legacy jp_session_active is purged on every write so old sessions don't linger.
81 | 🟡 | Medium | 14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04) | jobpilot/templates/landing.html, jobpilot/app.py, README.md | Google Sign-In button silently vanished when GOOGLE_CLIENT_ID was unset, with no startup warning or in-product hint. Admins debugging deploys had no signal that the env var was the cause. | Fixed | Rajesh | None (already met). Toggle via ?debug=1 query string on the landing URL. | (a) Startup logger.warning("GOOGLE_CLIENT_ID is not set; Google Sign-In is disabled.") in create_app(). (b) initGoogleSignIn() now branches: production users still see nothing (preserves clean UI), but ?debug=1 renders an inline dashed-border hint reading "Google Sign-In not configured — set GOOGLE_CLIENT_ID". (c) New **Enable Google Sign-In** section in README.md with Cloud Console steps, redirect URI guidance, and the ?debug=1 recipe. The actual rendering code was already correct (#75) — this issue closes the missing diagnostic loop.
82 | 🟢 | Low | 14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04) | jobpilot/static/js/app.js | clearSessionHistory() calls _persistSessionHistory(), but that function is never defined anywhere in app.js — clicking **Clear** in the in-session history panel throws ReferenceError. Likely fallout from the #72 "persist to sessionStorage" change where the helper was inlined and a stale call site remained. | Open | — | Decide whether session history should actually persist to sessionStorage (per the #72 analyst note) or stay in-memory only. Then either (a) implement _persistSessionHistory() (read/write jp_session_history) and matching restore-on-load, or (b) drop the call. Either path needs a single regression test exercising **Clear**. | Pre-existing latent bug; not user-visible until the **Clear** button is clicked, but should be cleaned up alongside the next history-panel touch.
83 | 🔴 | Critical | 14c. New — TTL Session + Google Visibility Sprint (added 2026-05-04) | jobpilot/templates/landing.html | submitAuth() finally block called switchTab(_authTab), which (per switchTab) sets auth-error.style.display = 'none'. Net effect: every failed login/register flashed the real error message for ~0 ms then hid it — user reported "can't login or create account, only demo works." Demo bypassed submitAuth() so it kept working. | Fixed | Rajesh | None (already met). | Replaced the destructive switchTab(_authTab) call with a button-only reset (btn.disabled = false; span.textContent = ...). The error banner now persists until the user retries. Backend (/api/auth/login, /api/auth/register) was healthy throughout — verified end-to-end via PowerShell Invoke-WebRequest (200 OK on register + login).

## 15. Core Backend Audit (added 2
15. Core/ Backend Audit (added 2026-05-05)
ID | Pri | Severity | Section | File | Finding | Status | Owner | Requirements | Analyst Note
84 | 🟠 | High | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/ai_engine.py | Default CLAUDE_MODEL is hard-coded to "claude-sonnet-4-6" — not a known Anthropic model SKU (the current released line is claude-sonnet-4-5-*). If CLAUDE_MODEL env var is unset, every AI call (score_ats, tailor_resume, apply_chat_instruction, generate_resume, improve_line, suggest_certifications, answer_screening_question) will 404 from the Anthropic API. Caught by the broad except Exception in each helper, so the user sees a generic "Error: …" string instead of an actionable message. | Open | — | Confirm the intended model id against the current Anthropic models list and either correct the literal or document the env override as mandatory in .env.example + README. Add a one-shot startup ping (e.g. client.models.retrieve(CLAUDE_MODEL)) that logs a clear warning if the SKU is unknown. | Likely a typo for claude-sonnet-4-5. Worth fail-fast at boot rather than silent per-call failures.
85 | 🟠 | High | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/auth_db.py | SECRET_KEY = os.environ.get("JWT_SECRET", "jobpilot-secret-change-in-production") falls back to a hard-coded string at module-import time. Even though app.py validates JWT_SECRET at startup (Issue #1 family), this module-level default means any test harness or one-off python -c "from core.auth_db import create_token; ..." invocation that imports without the env var will silently mint forge-able tokens. Defense-in-depth gap. | Open | — | Drop the fallback — raise RuntimeError("JWT_SECRET must be set") on import if the env var is missing AND we're not under pytest (gate via os.environ.get("PYTEST_CURRENT_TEST")). Pair with a short test asserting that the import fails without the env var in production mode. | Mirrors the well-known "insecure default" anti-pattern; the comment in the literal even says "change-in-production".
86 | 🟠 | High | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | fetch_job_description() calls _is_safe_external_url(url) (which resolves the host via getaddrinfo and checks every returned IP is public) and *then* calls requests.get(url, …) which re-resolves the host independently. A malicious DNS server can return a public IP for the first lookup and a private/loopback IP for the second (classic DNS rebinding TOCTOU), bypassing the SSRF guard added in #63. | Open | — | Pin the resolved IP from the pre-flight check and pass it to requests via a custom HTTPAdapter that overrides DNS, OR use a connection-level adapter that re-validates the resolved IP on each socket connect. Add a regression test using a custom resolver that flips the answer between calls. | High-impact, low-likelihood — exploitation requires the attacker to control the URL *and* DNS for the host; still worth closing because the guard is otherwise solid.
87 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | _SEARCH_CACHE: dict[tuple, tuple[float, list[dict]]] has no eviction. Every distinct (title, location, seniority, date_posted) tuple grows the dict forever; with frequent users searching varied roles the dict will grow unbounded over the process lifetime. Each entry can hold ~hundreds of job dicts (multi-KB each). | Open | — | Replace with functools.lru_cache(maxsize=128) on a thin wrapper, or add an explicit LRU sweep that drops entries with (now - ts) > _SEARCH_CACHE_TTL_SEC whenever the dict exceeds N entries. | Same pattern as #22 (in-memory usage counter) — fine for single-user dev, dangerous on Railway where the worker stays warm for hours.
88 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | All five search_apify_* functions (linkedin, indeed, glassdoor, ziprecruiter, modular) call _SESSION.post(...) against the module-level singleton, while every other scraper goes through the per-thread _session() introduced in Issue #25. Under ThreadPoolExecutor parallel fan-out from search_all_platforms, this re-opens the thread-safety hole #25 closed (mutating Session.headers mid-flight, shared connection pool contention). | Open | — | Replace _SESSION.post(...) with _session().post(...) in all five Apify functions. Audit the file with grep _SESSION\. to make sure no other call sites slipped through. | Mechanical fix; one-line per function. The discovery helper _discover_apify_actors is single-threaded at startup, so it can keep using _SESSION.
89 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | search_all_platforms fans 6 scrapers into a ThreadPoolExecutor and waits via as_completed(futures) with no overall deadline. The Apify run-sync-get-dataset-items calls have a 130-second per-request timeout. A single slow Apify actor stalls the entire /api/jobs/search response for 130s, with the user seeing only a spinning loader. | Open | — | Wrap as_completed in a budget — e.g. for fut in as_completed(futures, timeout=45): … and treat unfinished futures as failed sources (cancel + log). Surface a partial-results banner in the UI when sources timed out. | Pairs naturally with a circuit-breaker around Apify (per-actor failure counter that skips the actor for N seconds after K consecutive timeouts).
90 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/ai_engine.py, jobpilot/core/ai_engine.py, jobpilot/core/ai_engine.py | tailor_resume, apply_chat_instruction, generate_resume, and answer_screening_question all silently truncate inputs (resume_text[:6000], job_description[:3000], description[:2000], etc.) without surfacing any warning to the caller. Only score_ats reports truncation_warning. Long resumes / JDs lose tail content (often the most recent role) with no user feedback. | Open | — | Promote the truncation_warning pattern from score_ats into a shared helper, return it in every result dict, and surface a small banner in the UI when present. Limits should remain env-overridable (existing pattern). | Affects user trust: "why didn't AI mention my latest job?" — it never saw it.
91 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_reader.py | save_tailored_pdf swallows every WeasyPrint exception and silently falls back to the ReportLab path. The two paths produce visibly different PDFs (different fonts, spacing, no teal accent). End-users hitting a WeasyPrint misconfig (missing system libs, font failure) get a degraded PDF with no notice and no trail beyond a logger.warning. | Open | — | Either (a) propagate the WeasyPrint failure to the route layer and return a 502 with a clear message, or (b) include a one-line note in the response payload (pdf_renderer: "reportlab-fallback") and surface it in the UI when downloading. Add a smoke test that asserts WeasyPrint actually ran in the happy path. | Currently masks production-impacting deploy issues (e.g. Railway image missing libpango).
92 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/auth_db.py | create_user(email, password) does no validation at the DB layer — it lower()s the email and inserts whatever is provided. All format/length/strength enforcement happens in jobpilot/routes/auth.py; any other future caller (admin script, batch import, future API) bypasses the checks. | Open | — | Add minimal defense-in-depth in create_user: regex on email shape, len(password) >= 8 (or read from env), and reject obviously invalid inputs with ValueError. Do *not* duplicate the route-layer messages — those stay user-facing; this is the safety net. | Pairs naturally with #2 (input validation) once that work starts.
93 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | _get_apify_actor_ids() makes a live HTTP call to api.apify.com/v2/acts on first invocation. _APIFY_ACTORS_CACHE is populated only on success — there is no negative cache, so every job search during an Apify outage re-issues the discovery call (and pays its full 30s timeout). | Open | — | Cache *both* success and failure for at least 5 minutes. Even a _APIFY_ACTORS_CACHE = DEFAULT_APIFY_ACTORS.copy() populated on failure (timestamped) would prevent the per-request retry storm. | Symptom appears as "every search is suddenly slow" — hard to diagnose without log scraping.
94 | 🟡 | Medium | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_reader.py | read_resume(filename) builds the path as RESUMES_DIR / filename with no traversal sanitization. If any future caller passes a user-controlled filename containing .., the function will read arbitrary files inside the container. The route layer (jobpilot/routes/resume.py) currently sanitizes, but the helper is a footgun for any new caller. | Open | — | Reuse the existing _safe_stem() helper at the top of read_resume (or a parallel _safe_in_path()) and reject anything that resolves outside RESUMES_DIR. Mirror the pattern in _safe_out_path (resolve + startswith check). | Defense-in-depth — same hardening shape as #67/#65.
95 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/ai_engine.py | Dead-code typo: parts = after_later = after_label.split("✅ Change Log:", 1). The variable after_later is never read again — looks like a misspelling of after_label that the author meant to drop. Confusing on review and trips static analysis. | Open | — | Delete the after_later = chained assignment so the line reads parts = after_label.split("✅ Change Log:", 1). | Pure cleanup; no behavior change.
96 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/job_scraper.py | _get() always sleeps random.uniform(0.2, 0.6) before issuing the request, even when called from concurrent worker threads in search_all_platforms. With ~6 sources × up to 4 paginated requests each, this adds ~5–15 seconds of pure sleep per search wall-clock budget. | Open | — | Drop the unconditional sleep. If rate-limit jitter is needed, gate it per-host (only the slow sources — Adzuna and JSearch) and give it a tighter upper bound (≤200 ms). | Easy win for perceived search speed.
97 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_normalizer.py | normalize_job_title only matches whole-string lookups in JOB_TITLE_SYNONYMS. The dict has entries like "sr.", "sr ", "jr." that can never match, because no real title equals exactly "sr ". Same for the prefix entries — normalize_job_title("Sr Engineer") returns the input unchanged. | Open | — | Either (a) tokenize the title and apply prefix/suffix replacements (re.sub(r'\bsr\.?\b', 'senior', t, flags=I)), or (b) drop the dead dict entries and document that this helper is exact-match only. Pick one and add a unit test for "Sr Data Engineer". | Low-impact today (no caller uses this in production paths) but the dict is misleading on first read.
98 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/auth_db.py | decode_token() does payload["sub"] directly, raising KeyError if a JWT was signed with our secret but lacks the sub claim. The function's docstring promises only jwt.PyJWTError on failure, so callers who narrow their except will crash with an unhandled KeyError. | Open | — | Use payload.get("sub") and raise jwt.InvalidTokenError("sub claim missing") if None. Update the docstring or add a regression test. | Pure contract bug; trivial fix.
99 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_reader.py | TODO / refactor: save_tailored_pdf is ~270 lines including a near-duplicate _build_story_with_scale that re-parses content from scratch with parallel paragraph styles. Maintenance hazard — any new section type must be added in two places. | Open | — | Extract the line-walking parser into a single function that yields (kind, text) tuples, then have both the unscaled and scaled builders consume the same iterator and apply scale only at style construction. No behavior change expected. | Refactor candidate for the next time this file is opened for a real fix.
100 | 🟢 | Low | 15. Core/ Backend Audit (added 2026-05-05) | jobpilot/core/resume_reader.py | TODO / refactor: read_resume_bytes (added per Issue #67) and read_resume duplicate the PDF/DOCX extraction logic — the on-disk path opens files, the in-memory path wraps BytesIO, but the parser bodies are otherwise identical. | Open | — | Have read_resume(filename) open the file into bytes and delegate to read_resume_bytes(content, ext). Keep the txt fast-path. Adds one extra read for txt and zero for pdf/docx (which already buffer in memory). | Closes the rest of #67's deduplication intent.

## Roll-ups
Severity Roll-up
Pri | Severity | Total | Resolved | Won't Fix | WIP | Open
🔴 | Critical | 5 | 2 | 0 | 0 | 3
🟠 | High | 7 | 0 | 0 | 1 | 6
🟡 | Medium | 50 | 32 | 9 | 0 | 9
🟢 | Low | 38 | 29 | 2 | 0 | 7
| TOTAL | 100 | 63 | 11 | 1 | 25
Status Roll-up
Status | Count
Open | 25
WIP | 1
Fixed | 63
Won't Fix | 11
Contribution Tracker
Owner | Open | WIP | Fixed | Won't Fix | Total Touched
Rajesh | 0 | 1 | 63 | 0 | 64
— (unassigned) | 25 | 0 | 0 | 11 | 36

## Change Log
Date | Change | Issues Affected | Files Touched | Author
2026-05-04 | Initial corporate-format report generated; all 68 findings re-verified against working tree. | All | — | Review
2026-05-04 | Added **Sign out** button and **in-session History** panel to the resume editor (status bar). History captures upload, generate, tailor, ATS, chat, and download events with timestamps; cleared on reload / logout. | New feature (no prior CSV ID) | jobpilot/static/js/app.js, jobpilot/static/css/style.css | Rajesh
2026-05-04 | Removed legacy repo_issues.csv; this Markdown report is now the single source of truth. | Housekeeping | repo_issues.csv (deleted) | Rajesh
2026-05-04 | Re-checked report; refreshed shifted line numbers and logged 4 new findings (#69–#72) from the editor history/logout feature. | #43, #65 (line refs); #69–#72 (new) | jobpilot/static/js/app.js, jobpilot/static/css/style.css | Review
2026-05-04 | Added Pri (color-coded), Status, and Owner columns to every issue table for progress and contribution tracking. | All | — | Review
2026-05-04 | **Logout / session lifecycle hardening.** Resolved unresolved git merge conflict in logout(). Made hideAuthOverlay() null-safe so the topbar **Sign out** button now reveals on the jobs page. Added enforceSessionLifecycle() + jp_session_active marker so the user is auto-logged-out when the browser/tab closes (lands back on /, sees latest changelog). | Bug fix; partial mitigation of #71 | jobpilot/static/js/app.js, jobpilot/templates/index.html | Rajesh
2026-05-04 | **Low-priority remediation sprint.** Closed all 25 🟢 Low findings + #54 (🟡 Docker root). See per-issue Status / Analyst Note for details. | #8, #15, #16, #26, #28, #34, #35, #36, #38, #39, #40, #44, #45, #47, #48, #49, #50, #54, #55, #57, #58, #59, #62, #64, #66, #68, #70, #71, #72 | 11 files (see below) | Rajesh
2026-05-04 | **Low-risk Medium remediation sprint.** Closed 13 🟡 Medium findings (#5, #6, #10, #11, #18, #19, #21, #33, #46, #51, #52, #53, #65). All edits are small surface-area changes; no behavior change for happy paths. | #5, #6, #10, #11, #18, #19, #21, #33, #46, #51, #52, #53, #65 | jobpilot/app.py, jobpilot/core/ai_engine.py, jobpilot/core/resume_reader.py, jobpilot/routes/resume.py, jobpilot/routes/auth.py, jobpilot/routes/jobs.py, jobpilot/static/js/app.js | Rajesh
2026-05-04 | Added AGENTS.md at the repo root: codifies the contributor / agent workflow, owner-attribution rule (use Rajesh for fixes from this account), and the *update-don't-recreate* policy for this report. | Process | AGENTS.md | Rajesh
2026-05-04 | Added a **Requirements** column to every issue table. Open items list the concrete prerequisites to land the fix (env vars, libs, schema, tests, design decisions); fixed/won't-fix items read None (already met) or note the deferred dependency. | All | — | Rajesh
2026-05-04 | **Live Playwright UI sprint.** Drove the running app through every auth path + a full search; reproduced and fixed 7 bugs (1 🔴, 3 🟡, 3 🟢) under new Section 14b. Headline fix: every landing-page auth handler now writes sessionStorage.jp_session_active='1' so /app no longer wipes the token and bounces home (full auth lockout in fresh browsers). Also: Arbeitnow epoch dates now format correctly, /api/usage and /api/upload-resume requests now carry the bearer token, footer links stop scrolling to top, the orphan "or continue with" divider hides when Google is unconfigured, and the auth modal's leftover "12,000+" stat is gone. | #73, #74, #75, #76, #77, #78, #79 | jobpilot/templates/landing.html, jobpilot/core/job_scraper.py, jobpilot/static/js/app.js | Rajesh
2026-05-04 | **Phase 3 — Medium remediation sprint.** Mechanical print()→logger migration across 3 core modules; thread-local HTTP session + bounded retry adapter; SSRF allow-list for fetch_job_description; binary-search PDF auto-fit; shared read_resume_bytes parser; frontend _authTab/dead-code/theme-key cleanup; .env.example status flip. Also added a top-of-file warnings header per user request. | #12, #13, #14, #25, #29, #32, #41, #42, #43, #61, #63, #67 | jobpilot/core/ai_engine.py, jobpilot/core/job_scraper.py, jobpilot/core/resume_reader.py, jobpilot/routes/resume.py, jobpilot/static/js/app.js, REPO_ISSUES_REPORT.md | Rajesh
2026-05-04 | **Test & CI scaffolding.** Added pytest skeleton with app.test_client() fixture and 5 smoke tests covering health, landing render, demo login, registration validation, and the JWT guard on /api/jobs/search. Added matrix CI on python 3.11 / 3.12 running compileall + pytest, plus a separate Docker-build job. | #30 (WIP), #31 (Fixed) | tests/conftest.py, tests/test_auth_smoke.py, pytest.ini, requirements-dev.txt, .github/workflows/ci.yml | Rajesh
2026-05-04 | **Won't-Fix policy update.** Marked nine items 🚫 Won't Fix with explicit Requirements blocks documenting exactly what infra/design decisions must land first to reopen them. No code change. | #7, #20, #22, #23, #24, #27, #37, #56, #60 | REPO_ISSUES_REPORT.md | Rajesh
2026-05-04 | **TTL session + Google visibility sprint.** Replaced the tab-scoped sessionStorage.jp_session_active marker with a sliding localStorage.jp_session_expiry (7 d for real accounts, 24 h for demo) so logged-in users survive tab close + browser restart and only get logged out by sign-out, expiry, or browser "Clear site data". Added a ?debug=1-gated "GOOGLE_CLIENT_ID not configured" hint inside the auth modal, a startup logger.warning when the env var is unset, and an **Enable Google Sign-In** section in README.md. | #80, #81, #82 (new) | jobpilot/templates/index.html, jobpilot/templates/landing.html, jobpilot/static/js/app.js, jobpilot/app.py, README.md | Rajesh
2026-05-05 | **Login UX bugfix + Excel tracker.** Fixed submitAuth() in landing.html where the finally block called switchTab(_authTab) and immediately wiped the just-shown error banner — so failed login/register attempts (wrong password, email already taken, password < 6 chars) appeared to do nothing while only the demo button worked. Replaced the destructive call with a button-only reset so auth-error stays visible. Added scripts/build_issues_xlsx.py which parses this report and emits a color-coded, filterable REPO_ISSUES_REPORT.xlsx workbook (Legend / All Issues / per-section sheets / Roll-ups / Change Log). | #83 (new) | jobpilot/templates/landing.html, scripts/build_issues_xlsx.py, REPO_ISSUES_REPORT.xlsx | Rajesh
2026-05-05 | **Core/ backend audit.** Read-only walk through every file under jobpilot/core/ — ai_engine.py, auth_db.py, job_scraper.py, resume_normalizer.py, resume_reader.py, resume_templates.py. Logged 17 new findings (3 🟠 High, 8 🟡 Medium, 6 🟢 Low) under Section 15 below. Headlines: suspicious CLAUDE_MODEL default claude-sonnet-4-6 (likely 404s — verify against current Anthropic SKU list); auth_db.SECRET_KEY falls back to a hard-coded literal at module scope; SSRF guard in fetch_job_description has a DNS-rebinding TOCTOU window between resolution and request; _SEARCH_CACHE is unbounded; Apify scrapers regress #25 by reusing module-level _SESSION. No code changes in this pass — all 17 are 🆕 Open / unassigned for triage. Regenerated REPO_ISSUES_REPORT.xlsx. | #84–#100 (new) | — (review only) | Rajesh